## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirements definition and Project setup | All members | 28 | 29 | -1 | 1 |  |  |  | 103.6%
1.1 | User stories definition | All members | 3 | 4 | -1 | 1 | 2025-07-04 | 2025-07-05 | 2 | 133.3% | bar: WEEK 1 T to WEEK 1 W; WEEK 5 T to WEEK 5 F
1.2 | Lo-fi Mock up | All members | 8 | 7 | 1 | 1 | 2025-07-05 | 2025-07-07 | 3 | 87.5% | bar: WEEK 1 W to WEEK 2 F; WEEK 5 T to WEEK 5 F
1,3 | Architecture definition | Silvia Macagnano | 6 | 6 | 0 | 1 | 2025-07-10 | 2025-07-10 | 1 | 100% | bar: WEEK 5 T to WEEK 5 F
1,3,1 | Docker and Docker Compose set up | Antonella Mei | 2 | 2 | 0 | 1 | 2025-07-11 | 2025-07-12 | 2 | 100% | bar: WEEK 5 T to WEEK 5 F
1,3,2 | DB set up | Silvia Macagnano | 4 | 4 | 0 | 1 | 2025-07-12 | 2025-07-14 | 3 | 100% | bar: WEEK 5 T to WEEK 5 F
1,3,3 | Containers test | Antonella Mei | 5 | 6 | -1 | 1 | 2025-07-15 | 2025-07-18 | 4 | 120% | bar: WEEK 2 M to WEEK 3 T; WEEK 5 T to WEEK 5 F
2 | Application initialization | All members | 42 | 42 | 0 | 2 |  |  |  | 100%
2.1 | FP Authentication Service | Carlotta Ciani | 5 | 5 | 0 | 2 | 2025-08-04 | 2025-08-06 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W; WEEK 5 T to WEEK 5 F
2.2 | FP Question Service | Michela Fuselli | 6 | 6 | 0 | 2 | 2025-08-05 | 2025-08-06 | 2 | 100% | bar: WEEK 4 T to WEEK 4 W; WEEK 5 T to WEEK 5 F
2.3 | FP Voting Service | Chiara Maccabruno | 3 | 4 | -1 | 2 | 2025-08-05 | 2025-08-06 | 2 | 133.3% | bar: WEEK 4 T to WEEK 4 W; WEEK 5 T to WEEK 5 F
2.4 | DataBase implementation | Silvia Macagnano | 5 | 7 | -2 | 2 | 2025-08-19 | 2025-08-20 | 2 | 140% | bar: WEEK 5 T to WEEK 5 F
2.5 | Log in and Registration pages | Antonella Mei | 3 | 2 | 1 | 2 | 2025-08-19 | 2025-08-20 | 2 | 66.67% | bar: WEEK 5 T to WEEK 5 F
2.6 | Home page | Antonella Mei | 2 | 5 | -3 | 2 | 2025-08-20 | 2025-08-21 | 2 | 250% | bar: WEEK 5 T to WEEK 5 F
2.7 | Dashboard page | Michela Fuselli | 3 | 2 | 1 | 2 | 2025-08-22 | 2025-08-23 | 2 | 66.67% | bar: WEEK 5 T to WEEK 6 M
2.8 | Voting page | Chiara Maccabruno | 4 | 2 | 2 | 2 | 2025-08-23 | 2025-08-24 | 2 | 50% | bar: WEEK 5 T to WEEK 6 T
2.9 | Group page | Silvia Macagnano | 3 | 2 | 1 | 2 | 2025-08-24 | 2025-08-25 | 2 | 66.67% | bar: WEEK 5 T to WEEK 5 F; WEEK 6 T to WEEK 6 W
2.11 | Leaderboard page | Antonella Mei | 5 | 5 | 0 | 2 | 2025-08-25 | 2025-08-25 | 1 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 6 W
2.14 | Bug fixes | All members | 3 | 2 | 1 | 2 | 2025-08-26 | 2025-08-27 | 2 | 66.67% | bar: WEEK 5 T to WEEK 5 F; WEEK 6 R to WEEK 6 F
3 | Backend implementation | All members | 43 | 39 | 4 | 3 |  |  |  | 90.7%
3.1 | User registration implementation | Michela Fuselli | 8 | 7 | 1 | 3 | 2025-08-27 | 2025-08-27 | 1 | 87.5% | bar: WEEK 5 T to WEEK 5 F; WEEK 6 F
3,1,2 | CORS errors fix | Chiara Maccabruno | 6 | 4 | 2 | 3 | 2025-08-27 | 2025-08-28 | 2 | 66.67% | bar: WEEK 5 T to WEEK 5 F; WEEK 6 F to WEEK 7 M
3.2 | Groups page implementation | Silvia Macagnano | 5 | 5 | 0 | 3 | 2025-08-29 | 2025-08-29 | 1 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 7 T to WEEK 7 W
3.2.2 | Earning points implementation | Antonella Mei | 7 | 7 | 0 | 3 | 2025-08-30 | 2025-09-01 | 3 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 7 R to WEEK 8 F
3.3 | Login implementation | Carlotta Ciani | 4 | 3 | 1 | 3 | 2025-08-30 | 2025-08-30 | 1 | 75% | bar: WEEK 5 T to WEEK 5 F; WEEK 7 R
3.4 | User profile implementation | Carlotta Ciani | 3 | 3 | 0 | 3 | 2025-09-01 | 2025-09-02 | 2 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 7 F to WEEK 8 F
3,5,1 | Add group feature | Silvia Macagnano | 5 | 5 | 0 | 3 | 2025-09-03 | 2025-09-04 | 2 | 100% | bar: WEEK 5 T to WEEK 5 F
3.7 | Leaderboard implementation | Silvia Macagnano | 5 | 5 | 0 | 3 | 2025-09-05 | 2025-09-07 | 3 | 100% | bar: WEEK 5 T to WEEK 5 F
4 | Latest additions | All members | 15 | 15 | 0 |  |  |  |  | 100%
4.1 | Notification implementation | Michela Fuselli | 3 | 3 | 0 | 4 | 2025-09-08 | 2025-09-08 | 1 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 8 M to WEEK 9 M
4.2 | Join group by code implementation | Carlotta Ciani | 3 | 3 | 0 | 4 | 2025-09-08 | 2025-09-09 | 2 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 8 M to WEEK 9 T
4.3 | Bug fixes | All members | 9 | 9 | 0 | 4 | 2025-09-10 | 2025-09-14 | 5 | 100% | bar: WEEK 5 T to WEEK 5 F; WEEK 9 W to WEEK 10 T
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 128 | 154 | 3 | 53 | 2.4151 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | [6 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 128 | 125.5849 | 123.1698 | 120.7547 | 118.3396 | 115.9245 | 113.5094 | 111.0943 | 108.6792 | 106.2642 | 103.8491 | 101.434 | 99.0189 | 96.6038 | 94.1887 | 91.7736 | 89.3585 | 86.9434 | 84.5283 | 82.1132 | 79.6981 | 77.283 | 74.8679 | 72.4528 | 70.0377 | 67.6226 | 65.2075 | 62.7925 | 60.3774 | 57.9623 | 55.5472 | 53.1321 | 50.717 | 48.3019 | 45.8868 | 43.4717 | 41.0566 | 38.6415 | 36.2264 | 33.8113 | 31.3962 | 28.9811 | 26.566 | 24.1509 | 21.7358 | 19.3208 | 16.9057 | 14.4906 | 12.0755 | 9.6604 | 7.2453 | 4.8302 | 2.4151 | 2.7534e-14
[10 empty] | ESTIMATE | 128 | 125 | 122 | 120 | 117 | 114 | 111 | 108 | 106 | 104 | 102 | 99 | 96 | 94 | 91 | 88 | 85 | 82 | 78 | 76 | 72 | 70 | 66 | 64 | 60 | 58 | 56 | 53 | 52 | 49 | 46 | 44 | 42 | 40 | 38 | 36 | 33 | 29 | 26 | 25 | 23 | 20 | 18 | 16 | 14 | 11 | 8 | 5 | 4 | 3 | 2 | 0 | -1 | -3 | [6 empty] | 3125
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 3 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | [6 empty] | 132
[10 empty] | HRS REMAINING | 125 | 122 | 120 | 117 | 114 | 111 | 108 | 106 | 104 | 102 | 99 | 96 | 94 | 91 | 88 | 85 | 82 | 78 | 76 | 72 | 70 | 66 | 64 | 60 | 58 | 56 | 53 | 52 | 49 | 46 | 44 | 42 | 40 | 38 | 36 | 33 | 29 | 26 | 25 | 23 | 20 | 18 | 16 | 14 | 11 | 8 | 5 | 4 | 3 | 2 | 0 | -1 | -3 | -4 | [6 empty] | 2993
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET