## Product Backlog
Story Name | Story Description | Status
User Registration | As a user, I want to create an account using my email or social login, so that I can participate in voting sessions securely. | Done
Authentication and log in | As a user, I want to log in securely, so that my scores and history are saved. | Done
Reset password | As a user, I want to reset my password in case I forget it, so that I can regain access to my account. | Done
Edit profile | As a user, I want to edit my profile (e.g., name, profile picture), so that my friends can recognize me easily in the app. | Done
Logout | As a user, I want to log out of my account securely, so that I can protect my data on shared devices. | Done
Creating session | As a user, I want to create a voting session and invite my friends via a link or code, so that we can vote together and I can become the session leader. | Done
Joining session | As a user, I want to join an existing voting session using an invitation code or QRcode, so that I can participate in my friend’s game. | Done
Choosing a category | As a session leader, I want to choose a pre-defined category (e.g., "fun," "career," "future predictions") or enter a custom topic, so that the voting questions are relevant to my group. | Done
Asking for a category | As a user, I want to ask the system to generate a category randomly, so that the voting questions are relevant to my group. | Done
Self-voting disabled | As a session leader, I want to disable the self-voting choice, so that no participant can vote for themselves. | Done
Generating questions | As a user, I want the app to randomly generate a fun question based on our chosen topic, so that we always have different questions. | Done
Voting | As a user, I want to vote for one of my friends in response to the question, so that my choice is counted. | Done
leaderboard | As a user, I want to see a leaderboard of my friends, so that I can compare scores. | Done
home | As a user, I want to have all groups in the home page, so that I can access them easily. | Done

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Antonella
To Do | Doing | Carlotta
Done | Done | Chiara
| OK | Michela
Silvia

## Change Log
Version | Date | Changes
0.1.0 | 2017-11-06 | Removed the SCRUM board due to lack of usage and redundancy with Sprint Backlog.
0.1.1 | 2017-11-12 | Removed date columns on Sprint Backlog to simplify filling the data. Thus creating a manual step on Visible Progress to update the burndown chart.
0.1.2 | 2017-12-18 | Redacted conditions in readme
0.1.3 | 2017-12-21 | Included an easier way to update the burndown chart and included a FAQ
0.1.3.1 | 2018-01-18 | Fixed inconsistent formats on Sprint Backlog
0.1.4 | 2018-01-29 | Replaced SCRUM info page by a simpler setup page.
0.1.4.1 | 2018-02-01 | Fixed validation error
0.1.4.2 | 2018-02-01 | Included readme on the front
0.1.4.3 | 2018-06-07 | Eliminated unnecessary row on Burndown Chart due to a new version of charts in google spreadsheets
0.1.5 | 2018-09-07 | Removed abbreviations on comments with instructions
0.1.5.1 | 2018-10-07 | Adjusted Burndown Chart with formulas with date (just for display)
0.1.5.2 | 2018-08-15 | Removed the SCRUM editable file to maintain only one file, made notes with instructions on how to make your own copy on each page
0.1.5.3 | 2018-08-15 | Changed the word check out to Pull according to the reference document
0.1.6 | 2018-08-16 | Changed Colors, hidden pages
0.1.6.1 | 2018-08-21 | Added colors to tabs
0.1.6.2 | 2018-10-08 | Updated FAQ
0.1.6.3 | 2019-09-05 | Incuded reference to burndown charts
0.1.6.4 | 2019-10-09 | Changed features to user stories
0.1.7 | 2019-10-10 | References validation to named range

## FAQ
Question | Answer
How do I assign priority to Product Backlog Stories? | By dragging and dropping rows.
How do I assign priority to Sprint Backlog tasks? | By dragging and dropping rows.
How do I setup the burndown chart? | At the beginning of the sprint you setup the dates and adjust the sprint length by extending the sprint and dragging formulas as needed.
Why do the dates of the sprint have a formula? | Just to keep the dates as if the sprint was running, in practice the dates should be static and assigned by your Scrum Master.
How do I update the burndown chart? | Copy every day the "remaining effort" to the row named "Real" and you should see your chart updated.
How do I add features to the sprint backlog or product backlog? | It works better if you just write your task and drag it to the priority needed.
How do I make suggestions to this template? | You can make comments as needed. They will be reviewd and worked on or included here
How do I edit this file? | You can make your own copy with File/ Create a Copy or Download as a File. Also you are free to make comments to improve this file
How is this template made? | There are some simple formulas, data validation and conditional formatting that makes it possible.
How many stories can be added? | There is a limit of 100 sprint backlog and product backlog stories. You can add more if you edit the formulas and data validations.
Why there is no SCRUM board? | The information is very similar to Sprint Backlog, it was removed to have a simpler file and have an emphasis on the Burndown chart.
Why there is no time tracking? | The idea to estimate if the stories will be done by the end of the sprint, which can be done with the trendline on the burndown chart.
How can I add more than 9 development team members? | It's not recommended but you can add a row on the Options sheet and check on the Sprint Backlog if the drop down validation still works.